## agile_college_project_backlog
Sprint | Scrum Master | Assignee | Epic | MoSCoW Priority | User Story | Tasks / Notes
1 | Sharad | Deepershan | Research & Surveys | Must Have | As a researcher, I want to create a survey with 15 questions so that we can gather requirements from 60 people. | Create Google Form
1 | Sharad | Deepershan | Research & Surveys | Must Have | As a researcher, I want to distribute the survey link so that we hit our target demographic. | Share in college groups
1 | Sharad | Deepershan | Personas | Must Have | As an analyst, I want to define 5 target Personas so that our app caters to specific user needs. | Draft Alex, Priya, Tina, Ram, Nita
1 | Rihanna | Deepershan | Flow Charts | Must Have | As an analyst, I want to draw flowcharts for Persona journeys so that the app logic is visualized. | Use draw.io or lucidchart
1 | Rihanna | Rihanna | Personas | Should Have | As a designer, I want to create visual persona cards in Canva so the presentation looks professional. | Export as PNGs
1 | Rihanna | Sharad | Architecture | Must Have | As a developer, I want to initialize the GitHub repository so that all team members can collaborate. | Set up branches
1 | Sharad | Deepershan | Documentation | Must Have | As a project manager, I want to list all features in a MoSCoW matrix so that scope is clearly defined. | Must, Should, Could, Won't
1 | Sharad | Deepershan | Documentation | Must Have | As Audiophile Alex, I want high-quality audio routing so that my music sounds pristine. | Add to MoSCoW
1 | Rihanna | Rihanna | Surveys | Should Have | As an analyst, I want to summarize the 60 survey responses into pie charts so we can prove our requirements. | Add to presentation doc
1 | Rihanna | Sharad | Architecture | Must Have | As a developer, I want to set up the Firebase project so that our database infrastructure is ready. | Configure Firestore
2 | Deepershan | Rihanna | High Fidelity UI | Must Have | As a designer, I want to draft wireframes in Figma so that the layout is approved before high-fidelity design. | Focus on minimal layout
2 | Deepershan | Rihanna | High Fidelity UI | Must Have | As Party Host Priya, I want a dark-mode, slick interface so that the app looks good when playing music at night. | Figma UI Theme
2 | Deepershan | Rihanna | High Fidelity UI | Must Have | As Commuter Ram, I want large playback buttons so that I can easily pause music without looking closely. | Figma UI Components
2 | Sharad | Rihanna | High Fidelity UI | Must Have | As Tech-Savvy Tina, I want to see device connection status clearly so I know if the Pi is online. | Figma Status Indicator
2 | Sharad | Rihanna | High Fidelity UI | Should Have | As Casual Nita, I want to see album art prominently so that the app feels modern and engaging. | Figma Image placeholders
2 | Sharad | Sharad | Backend | Must Have | As a developer, I want to connect the Flutter app to Firebase Auth so that user sessions are managed. | Firebase Integration
2 | Deepershan | Deepershan | Documentation | Must Have | As a technical writer, I want to document the Firebase schema so that the database structure is clear. | Database design doc
2 | Deepershan | Rihanna | High Fidelity UI | Must Have | As a designer, I want to finalize all Figma screens so that the prototype is ready for pre-development testing. | Link Figma screens
2 | Sharad | Deepershan | User Testing | Must Have | As a researcher, I want to test the Figma prototype with 5 users so that we can fix UX issues early. | Prototype testing
2 | Sharad | Sharad | Backend | Must Have | As a developer, I want to write the Python script to stream music on the Pi so that core audio works. | Audio decoding logic
3 | Rihanna | Sharad | Flutter Client | Must Have | As a developer, I want to implement the Flutter base routing so that navigation matches the Figma design. | App scaffolding
3 | Rihanna | Sharad | Flutter Client | Must Have | As Party Host Priya, I want to see a scrollable list of songs so that I can pick the next track. | Build ListView
3 | Rihanna | Sharad | Flutter Client | Must Have | As Audiophile Alex, I want a volume slider on the main screen so I can adjust levels instantly. | Volume UI widget
3 | Deepershan | Sharad | Backend | Must Have | As Tech-Savvy Tina, I want the Pi to push its playback state to Firebase so the app stays in sync. | Firebase real-time DB
3 | Deepershan | Sharad | Flutter Client | Must Have | As Commuter Ram, I want to press play in the app and have the Pi start music instantly. | Firebase write commands
3 | Deepershan | Deepershan | iOS Build | Must Have | As a developer, I want to pull the GitHub repo onto the MacBook so that iOS compilation can begin. | Xcode setup
3 | Rihanna | Deepershan | iOS Build | Must Have | As Casual Nita, I want the app to run smoothly on my iPhone so I don't have to use an Android device. | Compile and run on Simulator
3 | Rihanna | Rihanna | Documentation | Must Have | As a team member, I want to compile the Sprint 1-3 progress report so that our documentation stays updated. | Word/PDF report
3 | Deepershan | Sharad | Backend | Must Have | As Tech-Savvy Tina, I want the Pi to automatically read ID3 tags so my song titles are correct. | Python ID3 extraction
3 | Deepershan | Sharad | Backend | Must Have | As a developer, I want to upload the local Pi tracklist to Firebase so the phone can read it. | Firebase sync script
4 | Sharad | Sharad | Edge Cases | Should Have | As Commuter Ram, I want the UI to show 'Offline' if the Pi loses power so I am not confused. | Connection state handling
4 | Sharad | Sharad | Edge Cases | Must Have | As Party Host Priya, I want the next song to play automatically when one finishes so the music doesn't stop. | Auto-advance logic
4 | Sharad | Sharad | Edge Cases | Could Have | As Audiophile Alex, I want to see the bitrate of the song playing so I know the quality. | UI text element update
4 | Rihanna | Rihanna | Presentation | Must Have | As a presenter, I want to draft the final slide deck in Canva so that we are ready for defense. | Import Figma & Flowcharts
4 | Rihanna | Deepershan | Persona Testing | Must Have | As a researcher, I want to find 5 people matching our Personas to test the actual coded app. | Recruit testers
4 | Rihanna | Deepershan | Persona Testing | Must Have | As a researcher, I want to record video of 'Tech-Savvy Tina' using the app so we have proof for the professor. | Shoot video
4 | Sharad | Deepershan | Persona Testing | Must Have | As a researcher, I want to record video of 'Casual Nita' using the app so we fulfill the video requirement. | Shoot video
4 | Sharad | Deepershan | Persona Testing | Must Have | As a researcher, I want to record video of 'Audiophile Alex' using the app so we fulfill the video requirement. | Shoot video
4 | Sharad | Sharad | Flutter Client | Must Have | As Casual Nita, I want the app to handle errors gracefully if a song file is corrupted. | Error state UI
4 | Rihanna | Deepershan | Persona Testing | Must Have | As a researcher, I want to record video of 'Party Host Priya' using the app to fulfill the video requirement. | Shoot video
5 | Deepershan | Rihanna | Feedback | Must Have | As a researcher, I want to create a final feedback Google Form so that we can evaluate user satisfaction. | Draft feedback questions
5 | Deepershan | Deepershan | Feedback | Must Have | As a researcher, I want the 5 Persona testers to fill out the feedback form after testing. | Collect form data
5 | Deepershan | Rihanna | Documentation | Must Have | As an analyst, I want to visualize the feedback data in charts so it can be added to the final report. | Create Canva charts
5 | Sharad | Sharad | Bug Fixes | Must Have | As Commuter Ram, I want the volume slider to not jump erratically so I don't blow out my speakers. | Debounce volume state
5 | Sharad | Deepershan | iOS Build | Must Have | As a developer, I want to create the final optimized iOS build on the MacBook so it runs without lag. | Release mode build
5 | Sharad | Sharad | Bug Fixes | Must Have | As Tech-Savvy Tina, I want the Pi script to restart on failure so the server is resilient. | Systemd / Docker restart policy
5 | Deepershan | Rihanna | Documentation | Must Have | As a project manager, I want to compile the final software documentation linking the GitHub repo. | Finalizing docs
5 | Deepershan | Rihanna | Presentation | Must Have | As a presenter, I want to embed the Persona testing videos into the Canva slides so the presentation flows well. | Video editing/embedding
5 | Sharad | Deepershan | Submission | Must Have | As a student, I want to ensure the 50-60 user stories are perfectly formatted in the final report. | Review CSV/Report
5 | Sharad | Sharad | Submission | Must Have | As a student, I want to review the final codebase and documentation so that the project defense goes perfectly. | Final review